## Sheet1
OXGHT_Cholera Response Activity Plan
[6 empty] | KEY | Complete/Ready/Standard Met
In Progress/Working towards meeting standards
Not started/ Standard not met
SN | ACTIVITY | SUB-ACTIVITIES | Oxfam / Partners | RESPONSIBILITY | RATIONALE | STATUS | ACTION POINT | November
[8 empty] | 1 | 2 | 3 | 4
| Epi Data Collection | Mapping active and hotspot areas |  | PHP | Better targetting limited resources
| Facility/Resources/Gap Mapping | Water Point Mapping per target area |  | PHE | Determine High Risk Water Point, Turbidity & Chlorination Strategy
|  | Latrine Mapping |  | PHE | Determine High Risk Areas
|  | Mapping of Health Facilities |  | Both | Determine high-risk facilities for IPC support & referral and health seeking pathway
| Staff Training | All Staff Training |  | Both
|  | Chlorinator Training |  | PHE
|  | Latrine Team Training |  | PHE
|  | Community Volunteer Trainings |  | PHP
|  | Partner training |  | PHP
| Coordination | Participating in national cholera coordination structure |  | PHP/PHE | Active participation in coordination mechanisms & influencing on raising community concerns & closing feedback loop
|  | Participating in area cholera coordination structure |  | PHP/PHE
WATER
| Framework Agreements: Water Trucking |  |  | PHE/Logs | Ensure stocks available for immediate response to evacuated/relocated population & ensure adequat chlorination of water
| Prepositioning - Water tanks, pipes, distribution system (tapstands) |  |  | PHE | Ensure stocks available for immediate response to evacuated/relocated population
| Bulk Treatment for High Turbidity Water |  |  | PHE | Ensure treatment facilities available for high turbidity water
| Prepositioning - Repair Materials |  |  | PHE | Ensure stocks available for rapid repair of damage to water systems
| Quick Repair Projects - Water Sources |  |  | PHE | Increase water points available to support supply of water
| Prepare and Equip Bucket Chlorination Teams | Training |  | PHE | Identify, train bucket chlorinators - sufficient for all non-centrally chlorinated water points
| Gather data on perceptions of Chlorinated water | Community Feedback |  | PHP | Determine any issues with chlorine levels and potential adaptations
| HH Water Quality Improvement Activities | Filter cloth distribution |  | PHP | For HHs using unsafe sources and for wells following rains (higher turbidity)
|  | Aquatab Distribution |  | PHP | If required to reduce risk of contamination
|  | Information and demonstration sessions |  | PHP
| Water Quality Monitoring | Bacteriological |  | PHE | Monitor non-chlorinated sources for potential e-coli contamination
|  | Distribution Point ( Residual Cholrine) |  | PHE | Ensure drinking water chlorine levels maintained within recommended levels |  | Weekly review by WASH team for highlighting problem areas
|  | Household (Residual Chlorine and HH Water Storage Monitoring) |  | PHP | Random sampling to inform HP on target areas for HHWQ improvement activities |  | Weekly review by WASH team for highlighting problem areas
SANITATION
| Sanitation survey |  |  | PHE | A full sanitation evaluating current status on saniation infrastrucute including looking for leakages from the pit latrine/ septic tank
| Prepositioning: Emergency Latrines |  |  | PHE | Increase sanitation coverage to minimise open defecation
| Prepositioning: Latrine repair equipment |  |  | PHE | Ensure stocks available for rapid repair of damage to latrines
| Prepositioning: Emergency Repair Teams |  |  | PHE | Ensure higher numbers on repair teams to support response
| Framework Agreements: Contractors, Latrine Construction |  |  | PHE/Logs | Ensure immediate response to evacuated/relocated population
| Prepositioning: Tarpaulin |  |  | PHE | For general use across WASH/HHs where needed
| Desluding team |  |  | PHE | Minimise the risk of overflowing/flooding latrines. Teams require training and safety equipment
| Decommissioning unsafe latrines | Decommissioning Latrines in Flood areas during winter season if needed |  | PHE | Minimise the risk of overflowing/Unsafe latrines
| Treatment and disposal of faecal sludge |  |  | PHE
| Upgrading Pre existing latrines | If needed |  | PHE | Minimise the risk of flooding latrines
| Formation of latrine user groups | Provision of latrine cleaning materials |  | PHP | Minimise the risk of latrines as transmission routes
| Feacal Sludge Management | Training |  | PHE | Train FSM workers on additional risks of desludging during outbreak and SOPs
|  | Provision of shower area, footbaths/sprays soap etc |  | PHE/PHP | Ensuring FSM workers can fully decontaminate after each days work
|  | Monitoring |  | PHE | Ensure FSM SOPs are adhered to to minimise transmission
| Latrine Cleaning team | Selection and Training |  | PHE | standby spray teams to respond to cases and routine spraying of latrines
| Monitoring |  |  | PHP | determine all latrines are clean and useable to minimise open defecation
HYGIENE PROMOTION & COMMUNITY ENGAGEMENT
| Community perceptions on cholera/AWD | Training/use of the CPT | all teams | To capture, analyse and use community's perceptions to adjust programming
| Coordination | Participation in RCCE/HP working group |  | PHP | Active participation in RCCE/ work on raising community concerns & closing feedback loop
| Development of IECs |  |  | PHP | Development of locally appropriate IECs
| Distribution of Hygiene Kits / Blanket coverage when possible for prevention |  |  | PHP | Distribution of hygiene kits prior to outbreak to support good hygiene practices
| Training | Community Mobilizers & Oxfam Staff |  | PHP | Training for community based staff on transmission, prevention, signs & symptoms
|  | CHWs/Other Community Based Staff |  | PHP | Training for community based staff on transmission, prevention, signs & symptoms
| Training for Stakeholders | Stakeholder mapping per block |  | PHP | Understanding of key influencers for engagement prior to and during response
|  | Training |  | PHP | Training for community stakeholders on transmission, prevention, signs & symptoms
| Community Action Planning | AWD |  | PHP | Community plans for engagement in prevention and response activities, to be monitored jointly with HPs
| Food Hygiene | Assessment at vendor level |  | PHP | To determine risky practices for food vendors, inform activities
|  | Training and Distribution of HW devices |  | PHP | Improve hygiene practices in markets
|  | Assesment of food hygiene practices at HH level |  | PHP | To determine risky practices, inform activities
| Prepositioning: Cholera Kits for CATI Approach | AWD/Cholera Prevention kits |  | PHP | For distribution to affected families in epidemics
|  | Hygiene Kits |  | PHP | For distribution to relocated/evacuated families